AI2-480 | Crawford 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-481 | Union City - French Road 12.5kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-482 | Copperstone-North Lebanon 230 kV IV |  | PA | Lebanon | Active | ME | 100 | 0 | 58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2023 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AI2-483 | Heath 69 kV |  | OH | Licking | Active | AEP | 22.4 | 0 | 13.44 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2023 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI2-484 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-485 | Bruin Junction - Petrol Junction 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AI2-486 | Bethelboro - Connellsville 25 kV |  | PA | Fayette | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AI2-487 | Kewanee-Hennepin Tap 138kV |  | IL | Bureau | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-488 | Electric Junction - Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-489 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-490 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 0 | 31.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AI2-491 | East Lima-Marysville 345kV |  | OH | Champaign | Active | AEP | 250 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-492 | Deer Creek-Fisher Body-Mullin 138kV |  | IN | Grant | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/26/2012 |  |  | N | No
AI2-493 | New Baltimore 115kV (Stony Creek) |  | PA | Somerset | Active | PENELEC | 52.5 | 0 | 18.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AI2-494 5271400 | PJM-TVA |  | N/A | N/A | Active | ComEd |  |  |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress | [5 empty] | N/A | N/A | [5 empty] | 3/24/2023 | 6/1/2025 | 6/1/2026 | [6 empty] | PP | No
AJ1-001 | Boydton DP 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-002 | North River Delivery Point 115 kV |  | VA | Rockingham | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-003 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-004 5279789 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress | [5 empty] | N/A | N/A | [5 empty] | 5/1/2023 | 6/1/2025 | 6/1/2026 | [6 empty] | PP | No
AJ1-005 5279793 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress | [5 empty] | N/A | N/A | [5 empty] | 5/1/2023 | 6/1/2025 | 6/1/2026 | [6 empty] | PP | No
AJ1-006 5279794 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn | [5 empty] | N/A | N/A | [5 empty] | 5/2/2023 | 6/1/2025 | 6/1/2026 |  | 12/6/2023 |  |  |  |  | PP | No
AJ1-007 5279795 | PJM-TVA |  | N/A | N/A | Active |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress | [5 empty] | N/A | N/A | [5 empty] | 5/2/2023 | 6/1/2025 | 6/1/2026 |  | 12/6/2023 |  |  |  |  | PP | No
AJ1-008 | Zimmer 345 kV |  | OH | Clermont | Active | DEOK | 800 | 800 | 692.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AJ1-010 | Racine - Sarah Lane 69 kV |  | WV | Mason | Active | AEP | 35 | 35 | 7.098 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/22/2023 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AJ1-011 | Waukegan Unit 7 CIR Transfer |  | IL | Lake | Active | ComEd | 328 | 328 | 328 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-012 | Waukegan Unit 8 CIR Transfer |  | IL | Lake | Active | ComEd | 354.4 | 354.4 | 354.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-013 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-014 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 260 | 260 | 260 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-015 | Larrabee Collector 230 kV |  | NJ | Monmouth | Active | JCPL | 1342 | 1342 | 1275 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/2/2023 | N/A | N/A |  |  |  | 5/1/2030 |  |  | N | No
AJ1-016 | Cambria Slope 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/7/2023 | N/A | N/A |  |  |  | 11/9/2028 |  |  | N | No
AJ1-018 | Bishopville – Worcester 138 kV |  | MD | Worcester | Active | DPL | 39 | 39 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2023 | N/A | N/A |  |  |  | 12/29/2028 |  |  | N | No
AJ1-019 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-020 | St. Johns – Woodpecker 115 kV |  | VA | Caroline | Active | Dominion | 86.38 | 86.38 | 51.828 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/15/2029 |  |  | N | No
AJ1-021 | Woodpecker – Slabtown 115 kV |  | VA | Caroline | Active | Dominion | 16.2 | 16.2 | 10.0584 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/15/2029 |  |  | N | No
AJ1-022 | Kerr Dam - Henderson NC 115 kV |  | VA | Mecklenburg | Active | Dominion | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 6/30/2027 |  |  | N | No
AJ1-023 | Trumbull 345 kV |  | OH | Trumbull | Active | ATSI | 1010 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AJ1-024 5294080 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2024 | 6/1/2025 |  | 11/6/2023 |  |  |  |  | PP | No
AJ1-025 5294081 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2024 | 6/1/2025 | [6 empty] | PP | No
AJ1-026 5294082 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2024 | 6/1/2025 | [6 empty] | PP | No
AJ1-027 5294084 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2026 | 6/1/2027 |  | 12/6/2023 |  |  |  |  | PP | No
AJ1-028 5294085 | PJM-TVA |  | N/A | N/A | Active |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2026 | 6/1/2027 | [6 empty] | PP | No
AJ1-029 5294090 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2026 | 6/1/2027 | [6 empty] | PP | No
AJ1-030 5294092 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2026 | 6/1/2027 | [6 empty] | PP | No
AJ1-031 5294093 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2027 | 6/1/2028 |  | 12/6/2023 |  |  |  |  | PP | No
AJ1-032 5294095 | PJM-TVA |  | N/A | N/A | Active |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2027 | 6/1/2028 | [6 empty] | PP | No
AJ1-033 5294096 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2027 | 6/1/2028 | [6 empty] | PP | No
AJ1-034 5294097 | PJM-TVA |  | N/A | N/A | Active |  |  | 250 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/5/2023 | 6/1/2027 | 6/1/2028 | [6 empty] | PP | No
AJ1-035 5294098 | PJM-TVA |  | N/A | N/A | Withdrawn |  |  | 500 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/6/2023 | 6/1/2024 | 6/1/2025 |  | 12/6/2023 |  |  |  |  | PP | No
AJ1-037 | Northeast - CP Crane 115 kV |  | MD | Baltimore County | Active | BGE | 500 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/8/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AJ1-038 | Penniman 34.5 kV |  | VA | York | Active | Dominion | 33 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2023 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
1003606 | FE-PJM |  | N/A | N/A | Withdrawn |  | 208 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/11/2008 | 11/1/2008 | 6/1/2009 | [6 empty] | FF | No
1041672 | PJM-TVA |  | N/A | N/A | Confirmed |  | 106 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
1041677 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
1041678 | PJM-TVA |  | N/A | N/A | Confirmed |  | 52 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2011 | [6 empty] | FF | No
1070958 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1070959 | PJM-FE |  | N/A | N/A | Confirmed |  | 42 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1070962 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 7/1/2009 | 7/1/2014 | [6 empty] | FF | No
1070966 | PJM-FE |  | N/A | N/A | Confirmed |  | 142 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 7/1/2009 | 7/1/2014 | [6 empty] | FF | No
1070967 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1091513 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 68 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/29/2009 | 2/1/2009 | 3/13/2026 | [6 empty] | FF | No
1091532 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 11 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/29/2009 | 2/1/2009 | 3/13/2026 | [6 empty] | FF | No
1091549 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 203 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/29/2009 | 5/1/2009 | 3/13/2026 | [6 empty] | FF | No
1115220 | PJM-AMIL |  | N/A | N/A | Confirmed |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/3/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1119633 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 142 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/10/2009 | 5/1/2009 | 5/1/2014 | [6 empty] | FF | No
1119653 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 118 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/10/2009 | 5/1/2009 | 5/1/2014 | [6 empty] | FF | No
1121578 | PJM-WEC |  | N/A | N/A | Confirmed |  | 10 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/12/2009 | 6/1/2009 | 6/1/2017 | [6 empty] | FF | No
1129395 | PJM-MECS |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2011 | [6 empty] | FF | No
1132597 | PJM-MECS |  | N/A | N/A | Confirmed |  | 25 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2010 | [6 empty] | FF | No
1132611 | PJM-FE |  | N/A | N/A | Confirmed |  | 38 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2012 | [6 empty] | FF | No
1134215 | FE-PJM |  | N/A | N/A | Annulled |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134216 | FE-PJM |  | N/A | N/A | Annulled |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134217 | FE-PJM |  | N/A | N/A | Annulled |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134219 | FE-PJM |  | N/A | N/A | Annulled |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1180629 | DUK-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/16/2009 | 10/1/2009 | 10/1/2014 | [6 empty] | FF | No
1251680 | PJM-TVA |  | N/A | N/A | Confirmed |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252025 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
1252026 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
1252090 | PJM-ALTW |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252092 | PJM-ALTW |  | N/A | N/A | Confirmed |  | 65 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252093 | PJM-ALTW |  | N/A | N/A | Confirmed |  | 149 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252097 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252098 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252099 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
4183678 | DUK-PJM |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/19/2012 | 10/1/2013 | 10/1/2018 | [6 empty] | FF | No
4244941 | PJM-TVA |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
500310 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 10/1/2006 | 4/1/2007 | [6 empty] | FF | No
500311 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 10/1/2006 | 1/1/2007 | [6 empty] | FF | No
501061 | PJM-NYIS |  | N/A | N/A | Withdrawn |  | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/501061_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 7/31/2006 | 6/1/2009 | 6/1/2019 | [6 empty] | FF | No
502025 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
502029 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
506017 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 2/1/2007 | [6 empty] | FF | No
507525 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
510924 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
510926 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
510942 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/510942_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 11/16/2006 | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510945 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510946 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510947 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510948 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520594 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520595 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520948 | PJM-NYIS |  | N/A | N/A | Confirmed |  | 26 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/520948_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
520949 | PJM-NYIS |  | N/A | N/A | Confirmed |  | 26 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2012 | [6 empty] | FF | No
520950 | PJM-NYIS |  | N/A | N/A | Confirmed |  | 26 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2012 | [6 empty] | FF | No
527594 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
527597 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
528018 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528020 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528021 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528022 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528023 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528024 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528028 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 6/1/2007 | [6 empty] | FF | No
529891 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/529891_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/8/2007 | 7/1/2009 | 7/1/2010 | [6 empty] | FF | No
530761 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
530778 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
530783 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
531601 | OVEC-PJM |  | N/A | N/A | Confirmed |  | 253 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/531601_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/531601_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/6/2007 | 10/1/2008 | 10/1/2013 | [6 empty] | FF | No
531604 | OVEC_PJM |  | N/A | N/A | Confirmed |  | 210 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/531604_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/531604_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
531616 | FE-PJM |  | N/A | N/A | Withdrawn |  | 2510 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
531617 | FE-PJM |  | N/A | N/A | Withdrawn |  | 1940 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
532696 | PJM-CIN |  | N/A | N/A | Withdrawn |  | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/532696_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/532696_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2007 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
533213 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
533260 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
539601 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/539601_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/20/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
539610 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
547020 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
547022 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
549214 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 12/1/2007 | [6 empty] | FF | No
549854 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 12/1/2007 | [6 empty] | FF | No
554476 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
554497 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
554504 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
554507 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
554509 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
554950 | LGEE-PJM |  | N/A | N/A | Confirmed |  | 63 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/554950_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 6/1/2008 | 6/1/2010 | [6 empty] | FF | No
555079 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555085 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555092 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555096 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
560490 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
560494 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
564527 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
564533 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
564538 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
564539 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
564543 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
564544 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
564878 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564884 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564895 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564938 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564940 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
565380 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/31/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
568552 | PJM.AP-PJM.DPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568554 | PJM.AP-PJM.PSEG |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568555 | PJM.AP-PJM.PSEG |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568556 | PJM.AP-PJM.PPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568557 | PJM.AP-PJM.PPL |  | N/A | N/A | Withdrawn |  | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
708103 | PJM-CPLE |  | N/A | N/A | Confirmed |  | 89 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/15/2007 | 11/1/2007 | 11/1/2008 | [6 empty] | FF | No
811046 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811048 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811061 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811067 | PJM_MECS |  | N/A | N/A | Confirmed |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811071 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811073 | PJM_MECS |  | N/A | N/A | Confirmed |  | 27 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811074 | PJM_MECS |  | N/A | N/A | Confirmed |  | 27 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811075 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811080 | PJM_MECS |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 2/1/2008 | 6/1/2009 | [6 empty] | FF | No
811082 | PJM_MECS |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811086 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811089 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811092 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811095 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811097 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811101 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811105 | PJM-AMIL |  | N/A | N/A | Withdrawn |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 4/1/2008 | 6/1/2009 | [6 empty] | FF | No
816850 | PJM-ALTE |  | N/A | N/A | Confirmed |  | 15 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/4/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
818965 | PJM-TVA |  | N/A | N/A | Confirmed |  | 180 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/10/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
818967 | PJM-TVA |  | N/A | N/A | Confirmed |  | 138 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/10/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
818976 | PJM-TVA |  | N/A | N/A | Confirmed |  | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/10/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
825955 | PJM-AMIL |  | N/A | N/A | Confirmed |  | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/30/2007 | 4/1/2008 | 6/1/2009 | [6 empty] | FF | No
847949 | PJM-MEC |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/27/2007 | 6/1/2008 | 6/1/2010 | [6 empty] | FF | No
863796 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 | [6 empty] | FF | No
863799 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 | [6 empty] | FF | No
866859 | ALTE-PJM |  | N/A | N/A | Withdrawn |  | 468 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
869320 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
869642 | PJM-FE |  | N/A | N/A | Confirmed |  | 42 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
869659 | PJM-FE |  | N/A | N/A | Confirmed |  | 142 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2008 | 7/1/2009 | [6 empty] | FF | No
869681 | PJM-FE |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
869803 | PJM-FE |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 7/1/2008 | 7/1/2009 | [6 empty] | FF | No
893173 | OVEC-PJM-FE |  | N/A | N/A | Confirmed |  | 462 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/31/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893692 | FE-PJM |  | N/A | N/A | Confirmed |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893694 | FE-PJM |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893702 | FE-PJM |  | N/A | N/A | Confirmed |  | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893704 | FE-PJM |  | N/A | N/A | Confirmed |  | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
894765 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 7/1/2008 | 7/1/2010 | [6 empty] | FF | No
894769 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 7/1/2008 | 7/1/2010 | [6 empty] | FF | No
894770 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 12/1/2008 | 12/1/2010 | [6 empty] | FF | No
894774 | PJM-CIN |  | N/A | N/A | Confirmed |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 12/1/2008 | 12/1/2010 | [6 empty] | FF | No
903384 | PJM-WEC |  | N/A | N/A | Confirmed |  | 320 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/25/2008 | 5/15/2010 | 5/31/2011 | [6 empty] | FF | No
988887 | PJM-CIN |  | N/A | N/A | Confirmed |  | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/10/2008 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
994856 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 138 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
994857 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
994858 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No

## Definitions-Mapping
Column Names from Data Tab
Project ID | Project/OASIS ID
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection request process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Generation Interconnection Agreement | After the project’s required study work is completed, PJM will tender a Generation Interconnection Agreement (“GIA”) to be executed by the Project Developer, the Transmission Owner, and PJM.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Submitted Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Project
Sliding Project